## Register
Feedback Register
Date | Time | Stakeholder Name | Method of Contact | Subject Area | Site Name | Details | Received | Status | Resolution Comment | Resolution | Date Resolved
2019-12-10 | 1:10 | Owen Webb | Email | Construction | West Wyalong | We’d like to offer our labour services for this solar farm. | 2019-12-10 | Action complete |  | Resolved | 31/12/2019
2021-02-15 | 4:05 | Anonymous | Email | Construction | West Wyalong | Hi Can you please advise who will be responsible for the procurement of the HV Substation equipment. We are a local manufacturer contracted to supply HV equipment (33/66/132kV Substation Disconnectors and earth switches) to Essential Energy. Look forward to hearing from you. | 2021-02-16 | Action complete |  | Resolved | 2021-02-16
2021-06-09 | 15:18 | David Johnson | Email | Construction | West Wyalong | Good afternoon My name is David Johnson of 1 Percy Street Wellington, I am interested in the possibility of gaining employment with the Snowy Hydro West Wyalong Solar farm with Lightsource BP. I have many different tickets including the Telehandler and am currently employed with Suntop Solar farm in Wellington.I would like information and contact numbers to apply for positions within your company. Regards | 2021-06-09 | Action complete |  | Resolved | 2021-06-10
2021-07-20 |  | Rebecca Douglas | Email | Construction | West Wyalong | Local resident raised concern that she could not use intersection, because it was closed for upgrade. Previously constructed driveway was unaccessable due to rain and poor Council road conditions | 2021-07-20 | Action complete | The Construction Manager met with complainant and offered a guided route through the work area to enable children access to a parked vehicle on the Newell Highway side of work area. | Resolved | 2021-07-21
2021-08-03 |  | Bland Shire Council, Jamie Harwood | Phone | Construction | West Wyalong | A complaint was received from Bland Shire Council on behalf of the Mayor that heavy vehicles have operated on a Sunday dropping equipment off at Blands Lane. He also indicated the driving behaviour of the drivers was poor. | 2021-08-03 | Action Complete | •There were no nearby noise receptors that would have been affected. •The complainant visually saw the trucks rather than being alerted by noise. Deliveries as part of the pre-construction activities were within the requirements work hours allowed under the Environmental Planning and Assessment (COVID-19 Development—Construction Work Days) Order (No 3) 2021. | Resolved | 2021-08-06
2021-08-03 |  | Bland Shire Council, Jamie Harwood | Phone | Construction | West Wyalong | A complaint was received via the Bland Shire Council that heavy vehicles had travelled along Bodells Lane whilst the Road was closed. | 2021-08-03 | Action Complete | •There were no nearby noise receptors that would have been affected. •The complainant visually saw the trucks rather than being alerted by noise. Deliveries as part of the pre-construction activities were within the requirements or work hours allowed under the Environmental Planning and Assessment (COVID-19 Development—Construction Work Days) Order (No 3) 2021. | Resolved | 2021-08-06
2021-09-22 |  | Brian Monaghan | Phone | Construction | West Wyalong | A number of strands along the fence line running parralel to Blands lane apears to be damaged along Blands lane. | 2021-09-22 | Action Complete | A meeting was held with the landowner and an agreement was reached for repairs to be undertaken to damaged portion of the fence line | Resolved | 2021-11-02
2022-05-09 |  | Sally Worner | Phone | Other | West Wyalong | Trenching of Non-Contestable works by Essential Energy has impacted the access to property along Blands lane due to trench subsidance. | 2022-05-09 | Action complete | A meeting was held with the landowner and an agreement reached to backfill and compact the trenches by adding additional road base to the material | Resolved | 2022-05-10
8686:112

## Data validation
Phone | Construction | Wellington | Very satisfied | Investigating
Letter | Operation | Mid-Murray | Satisfied | Investigation complete
Email | Environmental Matters | Mokoan & Mokoan Extension | Neither | Action proposed
| Stakeholder Engagement | Naring | Not satisfied | Action complete
| Other | West Wyalong | Escalating | Resolved
|  | Woolooga |  | Unresolved