## Sheet1
Feedback Register
Date | Time | Stakeholder Name | Method of Contact | Subject Area | Site Name | Details | Received | Status | Resolution Comment | Resolution | Date Resolved
2021-07-20 |  | Anonymous | Email | Construction | West Wyalong | Local resident raised concern that she could not use intersection, because it was closed for upgrade. Previously constructed driveway was unaccessable due to rain and poor Council road conditions | 2021-07-20 | Action complete | The Construction Manager met with complainant and offered a guided route through the work area to enable children access to a parked vehicle on the Newell Highway side of work area. | Resolved | 2021-07-21
2021-08-03 |  | Bland Shire Council | Phone | Construction | West Wyalong | A complaint was received from Bland Shire Council on behalf of the Mayor that heavy vehicles have operated on a Sunday dropping equipment off at Blands Lane. He also indicated the driving behaviour of the drivers was poor. | 2021-08-03 | Action Complete | •There were no nearby noise receptors that would have been affected. •The complainant visually saw the trucks rather than being alerted by noise. Deliveries as part of the pre-construction activities were within the requirements work hours allowed under the Environmental Planning and Assessment (COVID-19 Development—Construction Work Days) Order (No 3) 2021. | Resolved | 2021-08-06
2021-08-03 |  | Bland Shire Council | Phone | Construction | West Wyalong | A complaint was received via the Bland Shire Council that heavy vehicles had travelled along Bodells Lane whilst the Road was closed. | 2021-08-03 | Action Complete | •There were no nearby noise receptors that would have been affected. •The complainant visually saw the trucks rather than being alerted by noise. Deliveries as part of the pre-construction activities were within the requirements or work hours allowed under the Environmental Planning and Assessment (COVID-19 Development—Construction Work Days) Order (No 3) 2021. | Resolved | 2021-08-06
2021-09-22 |  | Anonymous | Phone | Construction | West Wyalong | A number of strands along the fence line running parralel to Blands lane apears to be damaged along Blands lane. | 2021-09-22 | Action Complete | A meeting was held with the landowner and an agreement was reached for repairs to be undertaken to damaged portion of the fence line | Resolved | 2021-11-02
2022-05-09 |  | Anonymous | Phone | Other | West Wyalong | Trenching of Non-Contestable works by Essential Energy has impacted the access to property along Blands lane due to trench subsidance. | 2022-05-09 | Action complete | A meeting was held with the landowner and an agreement reached to backfill and compact the trenches by adding additional road base to the material | Resolved | 2022-05-10
8686:112